## Sheet1
Risk name | Risk description | Risk probality of occurance | Risk impact / damage | Risk mitigation | Person in charge | Risk facor
Side tasks | Every tasks that comes up besides project tasks representing additional untracked effort | 100% | 8 | Explicit time scheduling | All | 8
Bad time estimation | Tasks take longer than expected leading to delay of workflow | 50% | 8 | Reestimate time plan regularly, reassign tasks if needed | Felix | 4
Documentation not detailed enough | Usage of web components is unclear to users with developer role | 70% | 5 | Independent testers | Sven | 3.5
Hardware problems | Laptop crashes multiple times while working, impacting workflow severely | 25% | 10 | Contacting IT Support as soon as possible | Joshua | 2.5
Implementation bugs, code issues | Not working code leads to unhappy users | 20% | 8 | Automated tests, codacy, code reviews through pull requests | All | 1.6
Security issues | When uploading an HTML file, all security risks have to be considered | 10% | 10 | White hacker, Codacy | Raphael | 1
Compliant with specifications | Due to the extend of specifications keeping the big picture in mind could become difficult | 25% | 3 | Feature files, regular meetings covering the project progress | Joshua | 0.75
Framework limitations | Extend of implementing features is limited due to framework limitations | 5% | 10 | Usage of other framework, fallback to native implementations | Raphael | 0.5
Browser limitations | Native browser support or changes in specifications of web platform APIs | 10% | 4 | Regular checks for new announcements | Felix | 0.4
Incompatible technologies | Collision of different frameworks | 5% | 6 | Read through documentation, do not use too many frameworks | All | 0.3
Maintainance of service providers | Availability of services depends on external providers | 1% | 10 | Backups | Sven | 0.1