## Sheet1
Time Estimation
Use Case | Time Spent In Hours | Function Points
Change Layout | 35.54 | 16.72
Change Panel Structure | 116.08 | 55.59
Change Profile | 41.25 | 59.84
Login/Register | 23 | 36.06
Estimated Time
Use Case | Estimated Time In Hours | Actual Time In Hours | Function Points
Widgets | 58.4522 | 168.67 | 46.62
Workbench | 59.706 | 72.5 | 47.62
Marketplace | 60.9598 | 121 | 48.62