## Sheet1
Time Estimation
| Function Points | Time Spent In Hours
Change Layout | 16.72 | 35.54
Change Panel Structure | 55.59 | 92.08
Change Profile | 59.84 | 46.75
Login/Register | 36.06 | 9.5
Estimated Time
| Estimated Time In Hours | Actual Time in Hours | Function Points
Widgets | 77.1608 | 168.66 | 46.62
Workbench | 78.8159 | 69.5 | 47.62
Marketplace | 80.471 | 121 | 48.62